## WorkingSheet
<----- | UNIQUE ROW CODE CREATION | [5 empty] | ----> | OPERATING PLAN 2021 | [8 empty] | % Complete | Notes | <-----ORIGINAL PLAN -----> |  |  | < ----- REPROJECTION -------> |  |  | <----- COMPLETED -----> |  |  | HEADER SELECTION CALCULATIONS | [8 empty] | Row to be
[28 empty] | Selected Person or Date[s] | [8 empty] | Visible?
UniqueRowCode | L1 | L2 | L3 | L4 | L5 | L6 | L7 | L | L01 | L02 | L03 | L04 | L05 | L06 | L07 | Person Responsible |  |  | Duration | Start | Finish | [7 empty] | L1 | L2 | L3 | L4 | L5 | L6 | L7 | RowCount |  | l | [6 empty] | l
RCHd | [7 empty] | LHd | L01HD | L02HD | L03HD | L04HD | L05HD | L06HD | L07HD | PRespHd | PercentCompHd | NotesHd | DurationOrigHd | StartOrigHd | FinishOrigHd | DurationReprojHd | StartReprojHd | FinishReprojHd | DurationCompHd | StartCompHd | FinishCompHd | SR1Hd | IDL1Hd | IDL2Hd | IDL3Hd | IDL4Hd | IDL5Hd | IDL6Hd | IDL7Hd | RowCountHd |  | L1 | L2 | L3 | L4 | L5 | L6 | L7 | L1 | L2 | L3 | L4 | L5 | L6 | L7 | RowVis?
S | S | [6 empty] | L1 | Student Services | [26 empty] | 2 | Yes | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
SM | S | M | [5 empty] | L2 |  | Marketing Sub-Project_2021 | [25 empty] | 2 | Yes | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
SM11 | S | M | 11 |  |  |  |  | L3 |  |  | Receive 100 enquiries between Feb 1st and 11 Dec 2021 |  |  |  |  | Unallocated | 50 |  | 334 days | 2021-01-15 | 2021-12-15 | [14 empty] | 0 |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
SM12 | S | M | 12 |  |  |  |  | L3 |  |  | FIRST QUARTER | [7 empty] | 92 days | 2021-01-15 | 2021-04-17 | [14 empty] | 2 | Yes | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
SM12A | S | M | 12 | A |  |  |  | L4 |  |  |  | MAILOUTS AND DATABASE | [6 empty] | 92 days | 2021-01-15 | 2021-04-17 | [14 empty] | 2 | Yes | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
SM12A1 | S | M | 12 | A | 1 |  |  | L5 |  |  |  |  | List big picture - Decide which lists get mailouts and calls |  |  | Andrew |  |  | 92 days | 2021-01-15 | 2021-04-17 | [14 empty] | 0 |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
SM12A2 | S | M | 12 | A | 2 |  |  | L5 |  |  |  |  | Mailouts to organisations that were not called on schedule |  |  | Andrew/Jasmine |  |  | 92 days | 2021-01-15 | 2021-04-17 | [6 empty] | Andrew/Jasmine | 5 | 6 | 8 | 9 | 11 | 11 | 11 | 4 | Yes | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
SM12A2A | S | M | 12 | A | 2 | A |  | L6 | [5 empty] | Organisations not called in last quarter must be sent letters in lieu of being called. Where this is sensible. |  | Jasmine | 20 | CABs done in March | 92 days | 2021-01-15 | 2021-04-17 | [6 empty] | Jasmine | 5 | 6 | 8 | 9 | 11 | 12 | 12 | 2 | Yes | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
SM12A2B | S | M | 12 | A | 2 | B |  | L6 | [5 empty] | Database team Leader sends list to Jasmine once data is received back from call centre and added to the main database. |  | Andrew |  |  | 92 days | 2021-01-15 | 2021-04-17 | [14 empty] | 0 |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
SM12A3 | S | M | 12 | A | 3 |  |  | L5 |  |  |  |  | Compile and complete lists for database |  |  | Andrew |  |  | 92 days | 2021-01-15 | 2021-04-17 | [14 empty] | 0 |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
SM12A3A | S | M | 12 | A | 3 | A |  | L6 | [5 empty] | Justices of the Peace |  | Andrew |  |  | 92 days | 2021-01-15 | 2021-04-17 | [14 empty] | 0 |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
SM12A3B | S | M | 12 | A | 3 | B |  | L6 | [5 empty] | Youth oriented groups |  | Andrew | 20 | Started. Volunteer AWOL | 92 days | 2021-01-15 | 2021-04-17 | [14 empty] | 0 |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
SM12A3C | S | M | 12 | A | 3 | C |  | L6 | [5 empty] | Teen parent units |  | Andrew | 100 |  | 92 days | 2021-01-15 | 2021-04-17 | [14 empty] | 0 |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
SM12A3D | S | M | 12 | A | 3 | D |  | L6 | [5 empty] | Pasifika organisations |  | Andrew | 0 | Not started | 92 days | 2021-01-15 | 2021-04-17 | [14 empty] | 0 |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
SM12A4 | S | M | 12 | A | 4 |  |  | L5 |  |  |  |  | Email introduction prior to calls by call centre | [5 empty] | 92 days | 2021-01-15 | 2021-04-17 | [14 empty] | 0 |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
SM12A4A | S | M | 12 | A | 4 | A |  | L6 | [5 empty] | Justices of the Peace |  | Andrew | 0 | No call centre | 92 days | 2021-01-15 | 2021-04-17 | [14 empty] | 0 |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
SM12A4B | S | M | 12 | A | 4 | B |  | L6 | [5 empty] | Youth oriented groups |  | Andrew | 0 | No call centre | 92 days | 2021-01-15 | 2021-04-17 | [14 empty] | 0 |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
SM12A4C | S | M | 12 | A | 4 | C |  | L6 | [5 empty] | Teen parent units |  | Andrew | 0 | No call centre | 92 days | 2021-01-15 | 2021-04-17 | [14 empty] | 0 |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
SM12A4D | S | M | 12 | A | 4 | D |  | L6 | [5 empty] | Pasifika organisations |  | Andrew | 0 | No call centre | 92 days | 2021-01-15 | 2021-04-17 | [14 empty] | 0 |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
SM12B | S | M | 12 | B |  |  |  | L4 |  |  |  | CALL CENTRE ACTIVITY | [6 empty] | 92 days | 2021-01-15 | 2021-04-17 | [14 empty] | 0 |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
SM12B1 | S | M | 12 | B | 1 |  |  | L5 |  |  |  |  | Call Centre big picture - decide order of calls for lists and other business | [5 empty] | 92 days | 2021-01-15 | 2021-04-17 | [14 empty] | 0 |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
SM12B2 | S | M | 12 | B | 2 |  |  | L5 |  |  |  |  | RYALT call centre | [5 empty] | 92 days | 2021-01-15 | 2021-04-17 | [14 empty] | 0 |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
SM12B2A | S | M | 12 | B | 2 | A |  | L6 | [5 empty] | Seek funding for calls made |  | Jo | 0 |  | 92 days | 2021-01-15 | 2021-04-17 | [14 empty] | 0 |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
SM12B2B | S | M | 12 | B | 2 | B |  | L6 | [5 empty] | Advertise for call centre operators |  | Rahul | 20 |  | 92 days | 2021-01-15 | 2021-04-17 | [14 empty] | 0 |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
SM12B2C | S | M | 12 | B | 2 | C |  | L6 | [5 empty] | Train call centre operators |  | Rahul | 0
[8 empty] | LFt | L01Ft | L02Ft | L03Ft | L04Ft | L05Ft | L06Ft | L07Ft | PRespFt | PercentCompFt | NotesFt | DurationOrigFt | StartOrigFt | FinishOrigFt | DurationReprojFt |  | FinishReprojFt | DurationActualFt |  | FinishActualHd | SR1HFt | IDL1Ft | IDL2Ft | IDL3Ft | IDL4Ft | IDL5Ft | IDL6Ft | IDL7Ft | RowCountFt
Formulas:
Duration = CONCATENATE(DAYS([Finish],[Start])," ","days")

## DropsStaff_Vols
***STAFF, VOLUNTEERS, TEAMS***
Jo | Manager
Jo/Jasmine
Jasmine | Volunteer Support Coord Admin
Rahul | Marketing
Rahul, Miriama | Marketing
Miriama | Marketing
Miriama/Tim | Volunteer Induction
Andrew | Database Team Leader
Andrew/Jasmine | Marketing Comms
CCTL [Vacancy] | Call Centre Leader
Ngareta | Ex Camp mgr/PA
Joanna | Student Coach Coordinator (Adults)
Joanna/Tim
Joanna/Jasmine
Ngareta | Ex Camp mgr/PA
Tim? | Youth Lead Tutor
E-recept leader [Vacancy] | E-recept leader
Suu Lam | Volunteer Coordinator
Tech Team Leader [Vacancy} | Tech Team Leader
Reshma
Byambaa/Jo
Byambaa
Unallocated
***END STAFF, VOLUNTEERS, TEAMS***