## Task_DB
Task ID | Task Name | Billing Type | Client Name | Assigned To | Priority | Accept Date | Est Total Hours | Hrs Worked to date | Balance Hrs | Est Compl Date | Task Status | Reporting Category | Task Due Wk | Notes | 41
2 | Plan swift take off | Hourly | Builder 1 | Estim01 | Normal | 2021-08-03 | 47 | 51 | -4 | 2021-08-11 | In Progress | Rep Cat 1 | 2
3 | Non planswift take off | Hourly | Builder 2 | Estim02 | Normal | 2021-08-04 | 47 | 20 | 27 | 2021-08-12 | In Progress | Rep Cat 2 | 2
4 | Checking estimate | Hourly | Builder 3 | Estim03 | Normal | 2021-08-05 | 47 | 20 | 27 | 2021-08-13 | In Progress | Rep Cat 3 | 2
5 | Sending out purchase orders | Hourly | Builder 4 | Estim04 | Normal | 2021-08-06 | 47 | 20 | 27 | 2021-08-16 | In Progress | Rep Cat 4 | 2
6 | Raising extra purchase orders | Hourly | Builder 5 | Estim05 | Normal | 2021-08-06 | 55 | 20 | 35 | 2021-08-16 | In Progress | Rep Cat 5 | 2
7 | Pricing Updates to databuild | Fixed | Builder 1 | Estim06 | Normal | 2021-08-09 | 70 | 20 | 50 | 2021-08-20 | In Progress | Rep Cat 6 | 2
8 | Setting up Catalogue for new builder | Hourly | Builder 2 | Estim06 | Normal | 2021-08-08 | 75 | 76 | -1 | 2021-08-23 | Completed | Rep Cat 7 | 3
9 | Ordering and receiving quotes | Hourly | Builder 3 | Estim02 | Normal | 2021-08-09 | 80 | 79 | 1 | 2021-08-23 | Completed | Rep Cat 8 | 2
10 | Plan swift take off | Fixed | Builder 4 | Estim07 | Normal | 2021-08-10 | 40 | 32 | 8 | 2021-08-17 | In Progress | Rep Cat 9 | 1 | Actually still lots of checking to do
11 | Checking estimate | Fixed | Builder 5 | Estim01 | Normal | 2021-08-12 | 50 | 48 | 0 | 2021-08-23 | In Progress | Rep Cat 10 | 2 | New note for this task.Updated 05/05/21
12 | Sending out purchase orders | Hourly | Builder 1 | Estim02 | Normal | 2021-08-13 | 55 | 0 | 55 | 2021-08-23 | Not Started | Rep Cat 1 | 2 | Not a lot of spending on this one.
13 | Raising extra purchase orders | Hourly | Builder 2 | Estim03 | Normal | 2021-08-16 | 60 | 10 | 50 | 2021-08-26 | In Progress | Rep Cat 2 | 2
14 | Pricing Updates to databuild | Hourly | Builder 3 | Estim04 | Normal | 2021-08-17 | 65 | 11 | 54 | 2021-08-30 | In Progress | Rep Cat 3 | 2
15 | Pricing Updates to databuild | Hourly | Builder 4 | Estim05 | Normal | 2021-08-17 | 65 | 12 | 53 | 2021-08-30 | In Progress | Rep Cat 4 | 2 | This is a new note for this task
16 | Ordering and receiving quotes | Hourly | Builder 5 | Estim06 | Normal | 2021-08-17 | 75 | 13 | 62 | 2021-08-31 | In Progress | Rep Cat 5 | 2
17 | Plan swift take off | Hourly | Builder 1 | Estim01 | Normal | 2021-08-18 | 80 | 78 | 2 | 2021-09-01 | Completed | Rep Cat 6 | 2
18 | Non planswift take off | Hourly | Builder 2 | Estim02 | Normal | 2021-08-19 | 90 | 78 | 12 | 2021-09-06 | In Progress | Rep Cat 7 | 3
19 | Checking estimate | Hourly | Builder 3 | Estim03 | Normal | 2021-08-20 | 100 | 100 | 0 | 2021-09-06 | Completed | Rep Cat 8 | 3
20 | Sending out purchase orders | Hourly | Builder 4 | Estim01 | Normal | 2021-08-09 | 110 | 43 | 67 | 2021-08-27 | In Progress | Rep Cat 9 | 3 | This task is half done. Waiting on something from Addison to complete.
21 | Raising extra purchase orders | Fixed | Builder 5 | Estim02 | Normal | 2021-08-10 | 110 | 51 | 59 | 2021-08-30 | In Progress | Rep Cat 10 | 3 | Add in some new notes here
22 | Last Task | Hourly | Builder 1 | Estim03 | Normal | 2021-08-12 | 110 | 0 | 110 | 2021-08-30 | Not Started | Rep Cat 1 | 3 | There once was a puppy called Cheeky, She loved to run and be freaky, She ran all the day and lost her way, but was found by her mummy-dog Tiki.
23 | New Task | Hourly | Builder 2 | Estim04 | Normal | 2021-08-27 | 80 | 0 | 80 | 2021-09-10 | Not Started | Rep Cat 2 | 2 | Takeoff with Cube Façade
24 | Quote 17 Ramblers Rd | Hourly | Builder 3 | Estim05 | Normal | 2021-08-31 | 42 | 0 | 42 | 2021-09-08 | Not Started | Rep Cat 3 | 2 | Notes notes notes notes and more notes
25 | Estimate debs house | Hourly | Builder 4 | Estim06 | Normal | 2021-08-31 | 60 | 0 | 60 | 2021-09-10 | Not Started | Rep Cat 4 | 2 | Notes
26 | Quote Simons new shop | Hourly | Builder 5 | Estim07 | Normal | 2021-08-31 | 60 | 0 | 60 | 2021-09-10 | Not Started | Rep Cat 5 | 2 | Notes
27 | Estimate something | Fixed | Builder 1 | Estim01 | Normal | 2021-09-02 | 80 | 0 | 80 | 2021-09-16 | Not Started | Rep Cat 6 | 2 | There are notes in this field
28 | Takeoff to Tasmania for a rest | Hourly | Builder 2 | Estim02 | Low | 2021-09-03 | 5 | 1 | 4 | 2021-09-06 | In Progress | Rep Cat 7 | 1 | Going with car on the ferry
29 | Quoting job for debs balcony | Fixed | Builder 3 | Estim03 | High | 2021-09-04 | 20 | 0 | 20 | 2021-09-07 | Not Started | Rep Cat 8 | 1 | No notes for this task
30 | Quote set of 4 National Health Homes | Hourly | Builder 4 | Estim04 | Urgent | 2021-09-05 | 7 | 0 | 7 | 2021-09-06 | Not Started | Rep Cat 9 | 1 | Details of this job
31 | Quote Cheekys teeth extraction | Hourly | Builder 5 | Estim05 | Normal | 2021-09-05 | 4 | 0 | 0 | 2021-09-06 | Not Started | Rep Cat 10 | 1 | The vet had better look after my fur baby
32 | Takeoff bills of material big house | Hourly | Builder 1 | Estim06 | Normal | 2021-09-06 | 70 | 0 | 0 | 2021-09-17 | Not Started | Rep Cat 1 | 2 | This is another task data test
33 | Quoting my favourite authors | Hourly | Builder 2 | Estim07 | Normal | 2021-08-05 | 15 | 8 | 0 | 2021-08-09 | Completed | Rep Cat 2 | 1 | Weil here it is the 06/08/21 and this task is completed.
34 | Quoting a brick dunny | Hourly | Builder 3 | Estim07 | Normal | 2021-09-06 | 15 | 0 | 0 | 2021-09-08 | Not Started | Rep Cat 3 | 1
35 | Takeoff for a queensland holiday | Hourly | Builder 4 | Estim01 | Normal | 2021-09-10 | 200 | 0 | 0 | 2021-10-15 | Not Started | Rep Cat 4 | 5 | Sun surf and sand and a good bottle of bubbly.
36 | This is a new estimating task | Hourly | Builder 1 | Estim02 | Normal | 2021-09-10 | 50 | 0 | 50 | 2021-09-20 | Not Started | Rep Cat 5 | 2 | There are no new notes here
37 | This is a new task for today | Hourly | Builder 2 | Estim03 | Normal | 2021-09-14 | 55 | 0 | 0 | 2021-09-23 | Not Started | Rep Cat 1 | 2 | There are no new notes for this task
38 | This is another new task for the week | Hourly | Builder 3 | Estim04 | Normal | 2021-09-14 | 26 | 0 | 0 | 2021-09-20 | Not Started | Rep Cat 1 | 1 | 0
39 | stop go stop go | Hourly | Builder 4 | Estim05 | Normal | 2021-09-14 | 2 | 0 | 0 | 2021-09-15 | Not Started | Rep Cat 1 | 1 | task notes
40 | and another one | Hourly | Builder 5 | Estim06 | Normal | 2021-09-14 | 3 | 0 | 0 | 2021-09-15 | Not Started | Rep Cat 1 | 1 | No notes here
Calendar

## Time_Card_DB
Assigned To | Task ID | Task Name | Date | Hours Worked | Task Status

## Admin
ADMIN SETTINGS
Due Status | Reporting Categories | Client | Client Status | Estim ID | Estimator | Current Hours Allocated | Email | Picture Name | EsEstim07ator Status |  | EsEstim07ating Workday Settings
Acceptance | [All Categories] | Builder 1 | Active | Estim01 | Buggs Bunny |  |  |  | Active | Standard work hours per EsEstim07ator per day | 8
Due wk 1 | Rep Cat 1 | Builder 2 | Active | Estim02 | Angel Wings |  |  |  | Active
Due wk 2 | Rep Cat 2 | Builder 3 | Active | Estim03 | Leasuresuit Larry |  |  |  | Active | Standard billing blocks per hour | 2
Due wk 3 | Rep Cat 3 | Builder 4 | Active | Estim04 | Mary Lamb |  |  |  | Active
Due wk 4 | Rep Cat 4 | Builder 5 | Active | Estim05 | Peter Rabbit |  |  |  | Active
Due wk 5 | Rep Cat 5 |  |  | Estim06 | Foghorn Leghorn |  |  |  | Active
Due wk 6 | Rep Cat 6 |  |  | Estim07 | Daffy Duck |  |  |  | Active | Staff Picture Location | C:\Users\Deb\Documents\_EXCEL\WorkflowRTE\PicturesRTE
Due wk 7 | Rep Cat 7
Due wk 8 | Rep Cat 8
Due wk 9 | Rep Cat 9 | [8 empty] | Staff Estim07e Cards Location | C:\Users\Deb\Documents\_EXCEL\WorkflowRTE\TimecardsRTE
Due wk 10 | Rep Cat 10